## Gantt Chart
PC12 CELL MORPHOLOGY ANALYSIS SYSTEM — GANTT CHART (WEEK 2-15)
WP No | Work Package Name | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Week Type |  | PRESENTATION | WORK | PRESENTATION | WORK | PRESENTATION | WORK | MIDTERM | PRESENTATION | WORK | PRESENTATION | WORK | PRESENTATION | WORK | ALL TOGETHER
WP1 | Preprocessing of Existing Dataset
WP1.1 | Existing Dataset — Cleanup & Relabeling | Week3: TEAM; Week4: TEAM
WP1.2 | Preprocessing + Augmentation + Data Split | Week3: EEE; Week4: EEE
WP2 | New Dataset Preparation
WP2.1 | New Dataset Preparation (Labeling) | Week9: TEAM; Week10: TEAM
WP2.2 | Preprocessing + Augmentation | Week10: TEAM; Week11: TEAM
WP3 | Segmentation
WP3.1 | Training Pipeline Setup + First Run | Week5: EEE
WP3.2 | DS-UNet Pilot Training (Architecture Validation) | Week6: EEE
WP3.3 | Segmentation Refinement (Balance, Resolution, HP) | Week7: EEE
WP3.4 | Full Dataset Training (Existing Data) | Week9: EEE
WP3.5 | Retrain / Evaluate with Expanded Dataset | Week10: EEE; Week11: EEE
WP4 | Post-processing & Analysis
WP4.1 | Post-processing Module | Week9: EEE; Week10: EEE
WP4.2 | Feature Extraction Module | Week11: EEE; Week12: EEE
WP4.3 | Evaluation (Metrics + Error Analysis) | Week12: EEE
WP4.4 | Improvement Loop (Error → Model Revision) | Week13: EEE
WP5 | XAI
WP5.2 | Full End-User Reasoning Layer + Validation | Week5: EEE; Week6: EEE; Week7: EEE; Week9: EEE; Week10: EEE; Week11: EEE; Week12: EEE; Week13: EEE
WP5.1 | XAI Method Selection + Prototype | Week6: EEE
WP6 | Interface Development
WP6.1 | Desktop UI Shell (Mock Data) | Week9: EEE; Week10: EEE; Week11: EEE
WP6.2 | Report Module (Template + Generator) | Week12: EEE; Week13: EEE
WP6.3 | Pipeline ↔ UI Integration + ONNX Packaging | Week14: EEE; Week15: EEE
WP6.4 | End-to-End Testing & Bug Fixing | Week15: TEAM
WP6.5 | Final Demo & Presentation Prep | Week15: TEAM
EEE | AI / ML development (EEE)
TEAM | Shared / team work
BME | Biomedical
Midterm week — no work
Presentation week (Week 2, 4, 6, 9, 11, 13)
All together (Week 15 — final integration)

## Group-A1
GROUP A1 — nnU-NET (AUTOMATIC CONFIGURATION, Dice+CE)
WP No | Work Package Name | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Week Type |  | PRESENTATION | WORK | PRESENTATION | WORK | PRESENTATION | WORK | MIDTERM | PRESENTATION | WORK | PRESENTATION | WORK | PRESENTATION | WORK | ALL TOGETHER
WP1 | Preprocessing of Existing Dataset
WP1.1 | Existing Dataset — Cleanup & Relabeling | Week3: TEAM; Week4: TEAM
WP1.2 | Preprocessing + Augmentation + Data Split | Week3: EEE; Week4: EEE
WP2 | New Dataset Preparation
WP2.1 | New Dataset Preparation (Labeling) | Week9: TEAM; Week10: TEAM
WP2.2 | Preprocessing + Augmentation | Week10: TEAM; Week11: TEAM
WP3 | Segmentation
WP3.1 | nnU-Net Data Format Conversion | Week5: EEE
WP3.2 | Automatic Configuration + Pilot Fold (ONNX Test) | Week6: EEE
WP3.3 | 5-Fold Cross-Validation Training | Week7: EEE
WP3.4 | Full Dataset Training (Existing Data) | Week9: EEE
WP3.5 | Retrain / Evaluate with Expanded Dataset | Week10: EEE; Week11: EEE
WP4 | Post-processing & Analysis
WP4.1 | Post-processing Module | Week9: EEE; Week10: EEE
WP4.2 | Feature Extraction Module | Week11: EEE; Week12: EEE
WP4.3 | Evaluation (Metrics + Error Analysis) | Week12: EEE
WP4.4 | Improvement Loop (Error → Model Revision) | Week13: EEE
WP5 | XAI
WP5.2 | Full End-User Reasoning Layer + Validation | Week5: EEE; Week6: EEE; Week7: EEE; Week9: EEE; Week10: EEE; Week11: EEE; Week12: EEE; Week13: EEE
WP5.1 | XAI Method Selection + Prototype | Week6: EEE
WP6 | Interface Development
WP6.1 | Desktop UI Shell (Mock Data) | Week9: EEE; Week10: EEE; Week11: EEE
WP6.2 | Report Module (Template + Generator) | Week12: EEE; Week13: EEE
WP6.3 | Pipeline ↔ UI Integration + ONNX Packaging | Week14: EEE; Week15: EEE
WP6.4 | End-to-End Testing & Bug Fixing | Week15: TEAM
WP6.5 | Final Demo & Presentation Prep | Week15: TEAM
EEE | AI / ML development (EEE)
TEAM | Shared / team work
BME | Biomedical
Midterm week — no work
Presentation week (Week 2, 4, 6, 9, 11, 13)
All together (Week 15 — final integration)

## Group-A2
GROUP A2 — DUAL-HEAD DS-UNET + SOFT-clDICE
WP No | Work Package Name | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Week Type |  | PRESENTATION | WORK | PRESENTATION | WORK | PRESENTATION | WORK | MIDTERM | PRESENTATION | WORK | PRESENTATION | WORK | PRESENTATION | WORK | ALL TOGETHER
WP1 | Preprocessing of Existing Dataset
WP1.1 | Existing Dataset — Cleanup & Relabeling | Week3: TEAM; Week4: TEAM
WP1.2 | Preprocessing + Augmentation + Data Split | Week3: EEE; Week4: EEE
WP2 | New Dataset Preparation
WP2.1 | New Dataset Preparation (Labeling) | Week9: TEAM; Week10: TEAM
WP2.2 | Preprocessing + Augmentation | Week10: TEAM; Week11: TEAM
WP3 | Segmentation
WP3.1 | Training Pipeline Setup + First Run | Week5: EEE
WP3.2 | DS-UNet Pilot Training (Architecture Validation) | Week6: EEE
WP3.3 | Segmentation Refinement (Balance, Resolution, HP) | Week7: EEE
WP3.4 | Full Dataset Training (Existing Data) | Week9: EEE
WP3.5 | Retrain / Evaluate with Expanded Dataset | Week10: EEE; Week11: EEE
WP4 | Post-processing & Analysis
WP4.1 | Post-processing Module | Week9: EEE; Week10: EEE
WP4.2 | Feature Extraction Module | Week11: EEE; Week12: EEE
WP4.3 | Evaluation (Metrics + Error Analysis) | Week12: EEE
WP4.4 | Improvement Loop (Error → Model Revision) | Week13: EEE
WP5 | XAI
WP5.2 | Full End-User Reasoning Layer + Validation | Week5: EEE; Week6: EEE; Week7: EEE; Week9: EEE; Week10: EEE; Week11: EEE; Week12: EEE; Week13: EEE
WP5.1 | XAI Method Selection + Prototype | Week6: EEE
WP6 | Interface Development
WP6.1 | Desktop UI Shell (Mock Data) | Week9: EEE; Week10: EEE; Week11: EEE
WP6.2 | Report Module (Template + Generator) | Week12: EEE; Week13: EEE
WP6.3 | Pipeline ↔ UI Integration + ONNX Packaging | Week14: EEE; Week15: EEE
WP6.4 | End-to-End Testing & Bug Fixing | Week15: TEAM
WP6.5 | Final Demo & Presentation Prep | Week15: TEAM
EEE | AI / ML development (EEE)
TEAM | Shared / team work
BME | Biomedical
Midterm week — no work
Presentation week (Week 2, 4, 6, 9, 11, 13)
All together (Week 15 — final integration)

## Group-A3
GROUP A3 — ViT-UNET + SimAM + TVERSKY
WP No | Work Package Name | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Week Type |  | PRESENTATION | WORK | PRESENTATION | WORK | PRESENTATION | WORK | MIDTERM | PRESENTATION | WORK | PRESENTATION | WORK | PRESENTATION | WORK | ALL TOGETHER
WP1 | Preprocessing of Existing Dataset
WP1.1 | Existing Dataset — Cleanup & Relabeling | Week3: TEAM; Week4: TEAM
WP1.2 | Preprocessing + Augmentation + Data Split | Week3: EEE; Week4: EEE
WP2 | New Dataset Preparation
WP2.1 | New Dataset Preparation (Labeling) | Week9: TEAM; Week10: TEAM
WP2.2 | Preprocessing + Augmentation | Week10: TEAM; Week11: TEAM
WP3 | Segmentation
WP3.1 | TransUNet Fork Setup + Pipeline | Week5: EEE
WP3.2 | ViT-UNet Pilot Training + Overfitting Check | Week6: EEE
WP3.3 | Segmentation Refinement (Scale Down If Needed) | Week7: EEE
WP3.4 | Full Dataset Training (Final ViT Scope) | Week9: EEE
WP3.5 | Retrain / Evaluate with Expanded Dataset | Week10: EEE; Week11: EEE
WP4 | Post-processing & Analysis
WP4.1 | Post-processing Module | Week9: EEE; Week10: EEE
WP4.2 | Feature Extraction Module | Week11: EEE; Week12: EEE
WP4.3 | Evaluation (Metrics + Error Analysis) | Week12: EEE
WP4.4 | Improvement Loop (Error → Model Revision) | Week13: EEE
WP5 | XAI
WP5.2 | Full End-User Reasoning Layer + Validation | Week5: EEE; Week6: EEE; Week7: EEE; Week9: EEE; Week10: EEE; Week11: EEE; Week12: EEE; Week13: EEE
WP5.1 | XAI Method Selection + Prototype | Week6: EEE
WP6 | Interface Development
WP6.1 | Desktop UI Shell (Mock Data) | Week9: EEE; Week10: EEE; Week11: EEE
WP6.2 | Report Module (Template + Generator) | Week12: EEE; Week13: EEE
WP6.3 | Pipeline ↔ UI Integration + ONNX Packaging | Week14: EEE; Week15: EEE
WP6.4 | End-to-End Testing & Bug Fixing | Week15: TEAM
WP6.5 | Final Demo & Presentation Prep | Week15: TEAM
EEE | AI / ML development (EEE)
TEAM | Shared / team work
BME | Biomedical
Midterm week — no work
Presentation week (Week 2, 4, 6, 9, 11, 13)
All together (Week 15 — final integration)