## Gantt Chart
PC12 HÜCRE MORFOLOJİSİ ANALİZ SİSTEMİ — GANTT CHART (WEEK 2–15)
İş Paketi No | İş Paketi Adı | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Hafta Tipi |  | SUNUM (EW) | OW | SUNUM (EW) | OW | SUNUM (EW) | OW | VİZE | SUNUM (EW) | OW | SUNUM (EW) | OW | SUNUM (EW) | OW | HEP BİRLİKTE
İP1 | Hazırlık & Planlama
İP1.1 | Literatür + mimari araştırması | bar: Week2
İP1.2 | Pipeline tasarımı & sınıf şeması kararı | bar: Week2 to Week7; Week9 to Week15
İP1.3 | Proje takip altyapısı — Gantt chart | bar: Week2 to Week3
İP1.4 | Veri envanteri + etiketleme protokolü | bar: Week2 to Week7; Week9 to Week15
İP1.5 | Proje takip altyapısı — Dashboard | bar: Week3
İP2 | Veri Hazırlığı
İP2.1 | İlk parti etiketleme (~%40 — pilot için) | bar: Week2 to Week7; Week9 to Week15
İP2.2 | Ön işleme + augmentasyon + veri bölme | bar: Week3 to Week4
İP2.3 | Kalan etiketleme (~%60) | bar: Week2 to Week7; Week9 to Week15
İP2.4 | Tutarlılık kontrolü + tam veri seti dondurma | bar: Week10
İP3 | Segmentasyon
İP3.1 | Eğitim boru hattı kurulumu + ilk koşu | bar: Week2 to Week7; Week9 to Week15
İP3.2 | DS-UNet pilot eğitimi (mimari doğrulama) | bar: Week6
İP3.3 | Segmentasyon iyileştirme (denge, çözünürlük, HP) | bar: Week2 to Week7; Week9 to Week15
İP3.4 | VİZE HAFTASI — çalışma yok | Week8: VİZE
İP3.5 | Tam veri seti eğitimi | bar: Week2 to Week7; Week9 to Week15
İP4 | Post-process & Analiz
İP4.1 | Post-process modülü | bar: Week9 to Week10
İP4.2 | Özellik çıkarımı modülü | bar: Week2 to Week7; Week9 to Week15
İP4.3 | Değerlendirme (metrikler + hata analizi) | bar: Week12
İP4.4 | İYİLEŞTİRME DÖNGÜSÜ (hata → model revizyonu) | bar: Week2 to Week7; Week9 to Week15
İP5 | XAI
İP5.1 | XAI-1 SPIKE (yöntem seçimi + pilotta koşu) | bar: Week6
İP5.2 | XAI-2: hata yorumlama (pilot üzerinde) | bar: Week2 to Week7; Week9 to Week15
İP5.3 | XAI-1 tam görselleştirme katmanı | bar: Week12
İP5.4 | XAI doğrulama (hata analiziyle çapraz) | bar: Week2 to Week7; Week9 to Week15
İP6 | Ürünleştirme
İP6.1 | Masaüstü arayüz iskeleti (mock veriyle) | bar: Week9 to Week11
İP6.2 | Rapor modülü (şablon + üretim motoru) | bar: Week2 to Week7; Week9 to Week15
İP6.3 | Pipeline ↔ UI entegrasyonu + ONNX paketleme | bar: Week14 to Week15
İP6.4 | Uçtan uca test & hata giderme | bar: Week2 to Week7; Week9 to Week15
İP6.5 | Final demo & sunum hazırlığı | bar: Week15
İP7 | Yeni Veri · tarih belirsiz
İP7.1 | Yeni veri seti teslim alımı | bar: Week2 to Week7; Week9 to Week15
İP7.2 | Yeni veri etiketleme (aynı protokol) | bar: Week2 to Week7; Week9 to Week15
İP7.3 | Eski/yeni doğruluk karşılaştırması & fine-tune | bar: Week2 to Week7; Week9 to Week15
ML | Yazılım / ML (kullanıcı)
EK | Ekip (Ortak)
BM | Biyomedikal
Vize haftası — çalışma yok
Tarih belirsiz (yeni veri setine bağlı)
SUNUM haftası (Week2,4,6,9,11,13 — EW)
HEP BİRLİKTE (Week15 — final entegrasyon)

## Group-A2
GROUP A2 — ÇİFT-BAŞLI DS-UNET + SOFT-clDICE
İş Paketi No | İş Paketi Adı | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Hafta Tipi |  | SUNUM (EW) | OW | SUNUM (EW) | OW | SUNUM (EW) | OW | VİZE | SUNUM (EW) | OW | SUNUM (EW) | OW | SUNUM (EW) | OW | HEP BİRLİKTE
İP1 | Hazırlık & Planlama
İP1.1 | Literatür + mimari araştırması | bar: Week2
İP1.2 | Pipeline tasarımı & sınıf şeması kararı | bar: Week2 to Week7; Week9 to Week15
İP1.3 | Proje takip altyapısı — Gantt chart | bar: Week2 to Week3
İP1.4 | Veri envanteri + etiketleme protokolü | bar: Week2 to Week7; Week9 to Week15
İP1.5 | Proje takip altyapısı — Dashboard | bar: Week3
İP2 | Veri Hazırlığı
İP2.1 | İlk parti etiketleme (~%40 — pilot için) | bar: Week2 to Week7; Week9 to Week15
İP2.2 | Ön işleme + augmentasyon + veri bölme | bar: Week3 to Week4
İP2.3 | Ortak protokol paketi | bar: Week2 to Week7; Week9 to Week15
İP2.4 | Kalan etiketleme (~%60) | bar: Week5 to Week7
İP2.5 | Tutarlılık kontrolü + tam veri seti dondurma | bar: Week2 to Week7; Week9 to Week15
İP3 | Segmentasyon
İP3.1 | Eğitim pipeline kurulumu + ilk koşu | bar: Week5
İP3.2 | DS-UNet pilot eğitimi (mimari doğrulama) | bar: Week2 to Week7; Week9 to Week15
İP3.3 | Segmentasyon iyileştirme (denge, çözünürlük, HP) | bar: Week7
İP3.4 | Tam veri seti eğitimi | bar: Week10 to Week11
İP4 | Post-process & Analiz
İP4.1 | Post-process modülü | bar: Week2 to Week7; Week9 to Week15
İP4.2 | Feature Extracting modülü | bar: Week11 to Week12
İP4.3 | Değerlendirme (metrikler + hata analizi) | bar: Week2 to Week7; Week9 to Week15
İP4.4 | İYİLEŞTİRME DÖNGÜSÜ (hata → model revizyonu) | bar: Week13
İP5 | XAI
İP5.1 | XAI-1 SPIKE (yöntem seçimi + pilotta koşu) | bar: Week2 to Week7; Week9 to Week15
İP5.2 | XAI-2: hata yorumlama (pilot üzerinde) | bar: Week9
İP5.3 | XAI-1 tam görselleştirme katmanı | bar: Week2 to Week7; Week9 to Week15
İP5.4 | XAI doğrulama (hata analiziyle çapraz) | bar: Week13
İP6 | Ürünleştirme
İP6.1 | Masaüstü arayüz iskeleti (mock veriyle) | bar: Week2 to Week7; Week9 to Week15
İP6.2 | Rapor modülü (şablon + üretim motoru) | bar: Week13 to Week14
İP6.3 | Pipeline ↔ UI entegrasyonu + ONNX paketleme | bar: Week2 to Week7; Week9 to Week15
İP6.4 | Uçtan uca test & hata giderme | bar: Week15
İP6.5 | Final demo & sunum hazırlığı | bar: Week2 to Week7; Week9 to Week15
ML | Yazılım / ML
EK | Ekip (Ortak)
BM | Biyomedikal
Vize haftası — çalışma yok
SUNUM haftası (Week2,4,6,9,11,13 — EW)
HEP BİRLİKTE (Week15 — final entegrasyon)

## Group-A1
GROUP A1 — nnU-NET (OTOMATİK YAPILANDIRMA, Dice+CE)
İş Paketi No | İş Paketi Adı | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Hafta Tipi |  | SUNUM (EW) | OW | SUNUM (EW) | OW | SUNUM (EW) | OW | VİZE | SUNUM (EW) | OW | SUNUM (EW) | OW | SUNUM (EW) | OW | HEP BİRLİKTE
İP1 | Hazırlık & Planlama
İP1.1 | Literatür + mimari araştırması | bar: Week2
İP1.2 | Pipeline tasarımı & sınıf şeması kararı | bar: Week2 to Week7; Week9 to Week15
İP1.3 | Proje takip altyapısı — Gantt chart | bar: Week2 to Week3
İP1.4 | Veri envanteri + etiketleme protokolü | bar: Week2 to Week7; Week9 to Week15
İP1.5 | Proje takip altyapısı — Dashboard | bar: Week3
İP2 | Veri Hazırlığı
İP2.1 | İlk parti etiketleme (~%40 — pilot için) | bar: Week2 to Week7; Week9 to Week15
İP2.2 | Ön işleme + augmentasyon + veri bölme | bar: Week3 to Week4
İP2.3 | Ortak protokol paketi | bar: Week2 to Week7; Week9 to Week15
İP2.4 | Kalan etiketleme (~%60) | bar: Week5 to Week7
İP2.5 | Tutarlılık kontrolü + tam veri seti dondurma | bar: Week2 to Week7; Week9 to Week15
İP3 | Segmentasyon
İP3.1 | nnU-Net veri formatı dönüştürme | bar: Week5
İP3.2 | Otomatik yapılandırma + pilot fold (ONNX testi) | bar: Week2 to Week7; Week9 to Week15
İP3.3 | 5-katlı çapraz doğrulama eğitimi | bar: Week7
İP3.4 | En iyi konfigürasyon + tam tahmin | bar: Week10 to Week11
İP4 | Post-process & Analiz
İP4.1 | Post-process modülü | bar: Week2 to Week7; Week9 to Week15
İP4.2 | Feature Extracting modülü | bar: Week11 to Week12
İP4.3 | Değerlendirme (metrikler + hata analizi) | bar: Week2 to Week7; Week9 to Week15
İP4.4 | İYİLEŞTİRME DÖNGÜSÜ (hata → model revizyonu) | bar: Week13
İP5 | XAI
İP5.1 | XAI-1 SPIKE (yöntem seçimi + pilotta koşu) | bar: Week2 to Week7; Week9 to Week15
İP5.2 | XAI-2: hata yorumlama (pilot üzerinde) | bar: Week9
İP5.3 | XAI-1 tam görselleştirme katmanı | bar: Week2 to Week7; Week9 to Week15
İP5.4 | XAI doğrulama (hata analiziyle çapraz) | bar: Week13
İP6 | Ürünleştirme
İP6.1 | Masaüstü arayüz iskeleti (mock veriyle) | bar: Week2 to Week7; Week9 to Week15
İP6.2 | Rapor modülü (şablon + üretim motoru) | bar: Week13 to Week14
İP6.3 | Pipeline ↔ UI entegrasyonu + ONNX paketleme | bar: Week2 to Week7; Week9 to Week15
İP6.4 | Uçtan uca test & hata giderme | bar: Week15
İP6.5 | Final demo & sunum hazırlığı | bar: Week2 to Week7; Week9 to Week15
ML | Yazılım / ML
EK | Ekip (Ortak)
BM | Biyomedikal
Vize haftası — çalışma yok
SUNUM haftası (Week2,4,6,9,11,13 — EW)
HEP BİRLİKTE (Week15 — final entegrasyon)

## Group-A3
GROUP A3 — ViT-UNET + SimAM + TVERSKY
İş Paketi No | İş Paketi Adı | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Hafta Tipi |  | SUNUM (EW) | OW | SUNUM (EW) | OW | SUNUM (EW) | OW | VİZE | SUNUM (EW) | OW | SUNUM (EW) | OW | SUNUM (EW) | OW | HEP BİRLİKTE
İP1 | Hazırlık & Planlama
İP1.1 | Literatür + mimari araştırması | bar: Week2
İP1.2 | Pipeline tasarımı & sınıf şeması kararı | bar: Week2 to Week7; Week9 to Week15
İP1.3 | Proje takip altyapısı — Gantt chart | bar: Week2 to Week3
İP1.4 | Veri envanteri + etiketleme protokolü | bar: Week2 to Week7; Week9 to Week15
İP1.5 | Proje takip altyapısı — Dashboard | bar: Week3
İP2 | Veri Hazırlığı
İP2.1 | İlk parti etiketleme (~%40 — pilot için) | bar: Week2 to Week7; Week9 to Week15
İP2.2 | Ön işleme + augmentasyon + veri bölme | bar: Week3 to Week4
İP2.3 | Ortak protokol paketi | bar: Week2 to Week7; Week9 to Week15
İP2.4 | Kalan etiketleme (~%60) | bar: Week5 to Week7
İP2.5 | Tutarlılık kontrolü + tam veri seti dondurma | bar: Week2 to Week7; Week9 to Week15
İP3 | Segmentasyon
İP3.1 | TransUNet fork kurulumu + pipeline hattı | bar: Week5
İP3.2 | ViT-UNet pilot eğitimi + overfitting kontrolü | bar: Week2 to Week7; Week9 to Week15
İP3.3 | Segmentasyon iyileştirme (gerekirse ViT kapsamı daraltılır) | bar: Week7
İP3.4 | Tam veri seti eğitimi (nihai ViT kapsamıyla) | bar: Week10 to Week11
İP4 | Post-process & Analiz
İP4.1 | Post-process modülü | bar: Week2 to Week7; Week9 to Week15
İP4.2 | Feature Extracting modülü | bar: Week11 to Week12
İP4.3 | Değerlendirme (metrikler + hata analizi) | bar: Week2 to Week7; Week9 to Week15
İP4.4 | İYİLEŞTİRME DÖNGÜSÜ (hata → model revizyonu) | bar: Week13
İP5 | XAI
İP5.1 | XAI-1 SPIKE (yöntem seçimi + pilotta koşu) | bar: Week2 to Week7; Week9 to Week15
İP5.2 | XAI-2: hata yorumlama (pilot üzerinde) | bar: Week9
İP5.3 | XAI-1 tam görselleştirme katmanı | bar: Week2 to Week7; Week9 to Week15
İP5.4 | XAI doğrulama (hata analiziyle çapraz) | bar: Week13
İP6 | Ürünleştirme
İP6.1 | Masaüstü arayüz iskeleti (mock veriyle) | bar: Week2 to Week7; Week9 to Week15
İP6.2 | Rapor modülü (şablon + üretim motoru) | bar: Week13 to Week14
İP6.3 | Pipeline ↔ UI entegrasyonu + ONNX paketleme | bar: Week2 to Week7; Week9 to Week15
İP6.4 | Uçtan uca test & hata giderme | bar: Week15
İP6.5 | Final demo & sunum hazırlığı | bar: Week2 to Week7; Week9 to Week15
ML | Yazılım / ML
EK | Ekip (Ortak)
BM | Biyomedikal
Vize haftası — çalışma yok
SUNUM haftası (Week2,4,6,9,11,13 — EW)
HEP BİRLİKTE (Week15 — final entegrasyon)